## 20200617
No | Issue/Changes | Cause/Measures | Similar Screens
1 | 3-1 Sorting was wrong. | it was sorted by PAYMENT_DAY. Now, it is changed to RunDate and Time.
2 | 3-4 header was reversed. | We did changed it before last release but it was reversed due to query changes.
3 | 0001/01/01 to 9999/12/31 shows no from date message. When inserting both. | 0001/01/01 was assumed as no date. It is now fixed. | 3-1, 3-4, 3-6
4 | In 3-7 datetime text boxes in grid do not accept yyyy/M/d format. | 3-7 validation before sending to API was left to changed to validate yyyy/M/d also.
5 | In 3-8, amount data max and min value not validated. | Max and Min amount has been added to money data type fields.
6 | Default minimum size. | All forms default minimum dimentions are now stored in config file (AmigoPaperWorkProcessSystem.exe.config). Property Name is "DefaultDimentions". Moreover, all controls from menu's anchors are removed. They will now stay in center regardless of the screen size. | All Forms
7 | 3A | 3A now has validation before inserting the same transaction data.
8 | 3-5 invoice order | Invoice calculation order was wrong. It is now fixed.

## 20200622
No | Issue/Changes | Cause/Measures | Similar Screens
1 | 3B, 35 Change Request | Modified the program
2 | Issue No 83 (no customer name showing), we are still fixing. |  | 3-2, 3-6
3 | Other Issues on excel sheet are fixed

## 20200625
No | Issue/Changes | Cause/Measures | Similar Screens
1 | 3A multiple file read has been implemented. | Modified the program
2 | 3A non-amigo duplicating Fixed | one field has left to check in query.
3 | 3B Allocated Completation Date has been correctly registered. | was => DEPOSIT_AMOUNT == ALLOCATED_MONEY (current allocated) now => DEPOSIT_AMOUNT == RECEIPT_DETAILS. ALLOCATED_MONEY (total allocated)
4 | 3-4 data grid do not display correctly after cancel and re-run 3B | removed PAYMENT_DAY group by

## 20200629
No | Issue/Changes | Cause/Measures | Similar Screens
1 | YEAR_MONTH is not sorted yet. | 1. RESERVE_INFO.RESERVE_ID has been added to keep track of RESERVES. 2. A VIEW has been added to keep query performance when sorting INVOICE_INFO.YEAR_MONTH 3. DIFF_ALLOCATION_AMOUNT Column is added to RESERVE_INFO to keep query performance optimal. | 3B, 3-5,RESERVE_INFO.RESERVE_ID, RESERVE_INFO.DIFF_ALLOCATION_AMOUNT
2 | 3-7, want to change display columns | Modify 1. DEPOSIT_AMOUNT to ALLOCATED_MOENY 2. DISPLAY RESERVE_INFO.DIFF_ALLOCATION_AMOUNT instead of substracting

## 20200701
No | Issue/Changes | Cause/Measures | Similar Screens
1 | 3-7 sorting not right | Re confirm and modify sorting | 2020-03-07
2 | 3-7 validating fields indexing wrong | Due to column changes in Issue No. 103. Now fixed with correct column for validating | 2020-03-07
3 | Issue No. 106 | Modify 3B flow to carry value according to new changes for YEAR_MONTH sorting | 3B
4 | 3-2 duplicating after moving some records | Due to DISTINCT UPDATED_DATE. It changes when modifying customer. | 2020-03-02
5 | 3-3 Messag Text wrong when moving to amigo with only one unmatched customer name. | added one condition to detect whether it is multiple or single select | 2020-03-03
6 | 3-7 validating | validating for STATUS_CASH_FORECAST_MM (between 1 and 12) added | 2020-03-07
7 | 3-7 need to show invoices even 3A and 3B is not executed. | Due to condition where ISNULL(RECEIPT_DETAILS.SEQ_NO,0) <> 0 | 2020-03-07

## 20200702
No | Issue/Changes | Cause/Measures | Similar Screens
1 | want to export excels in 3-7 without running 3A and 3B | Due to some search fields are NULL. ( NULL LIKE '%something'). Convert NULL to empty string when searching in query. | 3-7 excels
2 | want to set pink color to INVOICE_INFO.ALLOCATED_COMPLETION_DATE = NULL in 3-7 grid | Added condition to check ALLOCATED_COMPLETION_DATE in data grid cell formatting event. | 2020-03-07
3 | want to set transaction file name in 3A, RECEIPT_DETAIL and RECEIPT_DETAIL_NON_AMIGO | Modify API call parameter for 3A and assign TRANSACTION_FILE_NAME in 3A. | 3-A
4 | want to change RECEIPT_DETAIL.ALLOCATED_MONEY to RESERVE_INFO.RESERVE_AMOUNT | Change RECEIPT_DETAIL.ALLOCATED_MONEY to RESERVE_INFO.RESERVE_AMOUNT | 2020-03-07
5 | "No file found message" not showing after multiple file reading. | When sending multiple requests. codes are executed inside foreach loop. Therefore, no file fount exception is not occur when codes inside foreach loop are not executed. It is now added condition to check file count. | 3A
6 | STATUS_CASH_FORECAST_MM validation was 0 to 12 | Changed to between 1 to 12 now | 2020-03-07
7 | Want to add sorting in excel exports | Added sorting in excel exports | 2020-03-07

## 20200709
No | Issue/Changes | Cause/Measures | Similar Screens
1 | want to set ALLOCATION_COMPLETION_DATE = null when allocation cancel in 3-5 | modification request | 3-5 screen
2 | want to set YYYYMMDDhhmmss format to CSV output file name in 3-5 | was DDMMYYhhmmss | 3-5 screen
3 | set default file name in 3-7 excel outputs | modification request | 3-7 screen
4 | set date and currency format in 3-7 excel outputs | cell was not formatted | 3-7 screen
5 | left align to header in Acceout Reciable excel output | was middle align | 3-7 screen
6 | When moving all records at 3-2 and 3-3 total count is not updated in from | due to condition " if data.count>0" to update the form | 3-2, 3-3 screen
7 | 3-4 umatched count duplicateing when running 3B again | due to 3-5 ALLOCATION_COMPLETION_DATE was not set to null, this was not triggered before. It is now fixed. | 3-4 screen
8 | Allocation Quantity is not carried when running 3B again | due to 3-5 ALLOCATION_COMPLETION_DATE was not set to null, this was not triggered before. It is now fixed. | 3-B, 3-4,3-5
9 | want to remove password encryption | encryption for password is now removed | login

## 20200710
No | Issue/Changes | Cause/Measures | Similar Screens
1 | Dunning count Grid data fetching mastaken | fix Program | 3-7 screen
2 | cannot cancel allocate same billing code | Due to rollback when there is no billing code found. It is not skip when there is no record found. | 3-5 screen
| want to increase dunning count only when dunning date is modified. | modify program | 3-7 screen
| want to change cancel allocation logic | modify program | 3-5 screen

## 20200716
No | Issue/Changes | Cause/Measures | Similar Screens
1 | 3-4 show grid change request | It is now showing unmatched counts with no match count in same day | 3-4 screen
2 | 3-7 excel export year_month ("/") separating not correct when year_month contains CT | fix program | 3-7 screen
3 | 3-7 excel export year_month ("/") missing | fix program | 3-7 screen
4 | 3-7 excel export, want to format tax field as Text cell | modify program | 3-7 screen
5 | Dunning count increasing even if Dunning date is not edited. | Due to null value of Dunning Date in database. It is now conditioned to check if update value is Null or not. | 3-7 screen
6 | 3-5, remove SET RECEIPT_DETAIL.PAYMENT_DAY = NULL in cancel allocation | due to 3-4 change | 3-5 screen

## 20200717
No | Issue/Changes | Cause/Measures | Similar Screens
1 | dunning count updating when dunning date is not null | modify condition when dunning date is not null | 3-7 screen

## 20200723
No | Issue/Changes | Cause/Measures | Similar Screens
1 | web service reject when there is too many records | added setting to configure max length in Web.config file
2 | want to add condition to allocated invoices for each receipt | program modified | 3B
3 | want to set null at blank cells at excel exports | check if empty and set nothing if data is empty | 3-7 excels
4 | want to add additional condition to check duplicate in 3A (TRANSACTION_DATE and TRANSACTION_NO) | program modified | 3A
5 | add more condtion in Account receivable report | added more condition WHERE INVOICE_INFO.ALLOCATED_COMPLETION_DATE Is Not Null | 3-7 account receivable excel
6 | want to insert ・Transfer message ・Note ・Number of cases when executing 3A | program modified | 3A
7 | CUSTOMER_MASTER table removed from 3-5 query and change CUSTOMER_MASTER.COMPANY_NAMEto INVOICE_INFO.BILL_SUPPLIER_NAME | program modified | 3-5 screen

## 20200727
No | Issue/Changes | Cause/Measures | Similar Screens
1 | Schedule payment excel output condition | added "CASE WHEN ISNULL(ALLOCATED_COMPLETION_DATE,'') = '' THEN NULL ELSE FORMAT(STATUS_ACTUAL_DEPOSIT_DATE, 'yyyy/MM/dd') END" condition for STATUS_ACTUAL_DEPOSIT_DATE column | 3-7 screen

## 20200812
No | Issue/Changes | Cause/Measures | Similar Screens
1 | "EFFECTIVE_DATE <= GETDATE() ORDER BY EFFECTIVE_DATE DESC" condition added | [WEB SERVICE] 3-2 and 3-6 report query modified | 3-2 (join with CUSTOMER_MASTER), 3-6 (join with CUSTOMER_MASTER)
3-6 Query
DECLARE @FromDate DATETIME2 = '@ParaFrom' @ToVariable SELECT DISTINCT SEQ_NO,FORMAT (RUN_DATE_TIME, 'yyyyMMddHHmm') AS DateTimeID,CUSTOMER_NAME,DEPOSIT_AMOUNT, ISNULL(BILL_COMPANY_NAME,'') BILL_COMPANY_NAME,ISNULL(BILL_CONTACT_NAME,'') BILL_CONTACT_NAME, ISNULL(BILL_PHONE_NUMBER,'') BILL_PHONE_NUMBER, ISNULL(BILL_MAIL_ADDRESS,'') BILL_MAIL_ADDRESS FROM (SELECT * FROM RECEIPT_DETAILS WHERE --FORMAT (RUN_DATE_TIME, 'yyyyMMddHHmm') = @DateTimeID CONVERT(varchar(10),PAYMENT_DAY,112) >= CONVERT(varchar(10),@FromDate,112) @ToCondition AND ALLOCATED_QUANTITY=0 AND RUN_RESULT =1 )RCP LEFT JOIN ( SELECT BILL_COMPANY_NAME, BILL_CONTACT_NAME, BILL_PHONE_NUMBER, BILL_MAIL_ADDRESS, CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-1],CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-2], CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-3], CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-4] FROM CUSTOMER_MASTER, (SELECT MAX(EFFECTIVE_DATE) EFFECTIVE_DATE, [BILL_BANK_ACCOUNT_NAME-1], [BILL_BANK_ACCOUNT_NAME-2], [BILL_BANK_ACCOUNT_NAME-3],[BILL_BANK_ACCOUNT_NAME-4] FROM CUSTOMER_MASTER WHERE EFFECTIVE_DATE <= GETDATE() GROUP BY [BILL_BANK_ACCOUNT_NAME-1], [BILL_BANK_ACCOUNT_NAME-2], [BILL_BANK_ACCOUNT_NAME-3],[BILL_BANK_ACCOUNT_NAME-4] ORDER BY EFFECTIVE_DATE DESC OFFSET 0 ROWS )TEMP WHERE CUSTOMER_MASTER.EFFECTIVE_DATE = TEMP.EFFECTIVE_DATE ) Customer ON ( TRIM(CONVERT(nvarchar(50),Customer.[BILL_BANK_ACCOUNT_NAME-1])) = TRIM(CONVERT(nvarchar(50),RCP.CUSTOMER_NAME)) OR TRIM(CONVERT(nvarchar(50),Customer.[BILL_BANK_ACCOUNT_NAME-2])) = TRIM(CONVERT(nvarchar(50),RCP.CUSTOMER_NAME)) OR TRIM(CONVERT(nvarchar(50),Customer.[BILL_BANK_ACCOUNT_NAME-3])) = TRIM(CONVERT(nvarchar(50),RCP.CUSTOMER_NAME)) OR TRIM(CONVERT(nvarchar(50),Customer.[BILL_BANK_ACCOUNT_NAME-4])) = TRIM(CONVERT(nvarchar(50),RCP.CUSTOMER_NAME)) ) ORDER BY CUSTOMER_NAME ASC
3-2 Query
SELECT DISTINCT Amigo.SEQ_NO,Amigo.CUSTOMER_NAME,Amigo.DEPOSIT_AMOUNT,Customer.BILL_COMPANY_NAME FROM (SELECT *,FORMAT(RUN_DATE_TIME, 'yyyyMMddHHmm') AS DateTimeID FROM RECEIPT_DETAILS WHERE Run_Result = 1 AND FORMAT(RUN_DATE_TIME, 'yyyyMMddHHmm')= @DTMID) Amigo LEFT JOIN ( SELECT BILL_COMPANY_NAME, CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-1],CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-2], CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-3], CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-4] FROM CUSTOMER_MASTER, (SELECT MAX(EFFECTIVE_DATE) EFFECTIVE_DATE, [BILL_BANK_ACCOUNT_NAME-1], [BILL_BANK_ACCOUNT_NAME-2], [BILL_BANK_ACCOUNT_NAME-3],[BILL_BANK_ACCOUNT_NAME-4] FROM CUSTOMER_MASTER WHERE EFFECTIVE_DATE <= GETDATE() GROUP BY [BILL_BANK_ACCOUNT_NAME-1], [BILL_BANK_ACCOUNT_NAME-2], [BILL_BANK_ACCOUNT_NAME-3],[BILL_BANK_ACCOUNT_NAME-4] ORDER BY EFFECTIVE_DATE DESC OFFSET 0 ROWS )TEMP WHERE CUSTOMER_MASTER.EFFECTIVE_DATE = TEMP.EFFECTIVE_DATE ) Customer ON ( TRIM(CONVERT(nvarchar(50),Customer.[BILL_BANK_ACCOUNT_NAME-1])) = TRIM(CONVERT(nvarchar(50),Amigo.CUSTOMER_NAME)) OR TRIM(CONVERT(nvarchar(50),Customer.[BILL_BANK_ACCOUNT_NAME-2])) = TRIM(CONVERT(nvarchar(50),Amigo.CUSTOMER_NAME)) OR TRIM(CONVERT(nvarchar(50),Customer.[BILL_BANK_ACCOUNT_NAME-3])) = TRIM(CONVERT(nvarchar(50),Amigo.CUSTOMER_NAME)) OR TRIM(CONVERT(nvarchar(50),Customer.[BILL_BANK_ACCOUNT_NAME-4])) = TRIM(CONVERT(nvarchar(50),Amigo.CUSTOMER_NAME)) ) ORDER BY Amigo.CUSTOMER_NAME ASC
3-3 Check Query
SELECT COMPANY_NO_BOX from CUSTOMER_MASTER WHERE (TRIM(CONVERT(nvarchar(50),CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-1])) = @BANK_ACCOUNT_NAME OR TRIM(CONVERT(nvarchar(50),CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-2])) = @BANK_ACCOUNT_NAME OR TRIM(CONVERT(nvarchar(50),CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-3])) = @BANK_ACCOUNT_NAME OR TRIM(CONVERT(nvarchar(50),CUSTOMER_MASTER.[BILL_BANK_ACCOUNT_NAME-4])) = @BANK_ACCOUNT_NAME) AND EFFECTIVE_DATE <= GETDATE() ORDER BY EFFECTIVE_DATE DESC

## 20200817
No | Issue/Changes | Cause/Measures | Similar Screens
1 | "EFFECTIVE_DATE <= GETDATE() ORDER BY EFFECTIVE_DATE DESC" condition query not wroking propely due to BANK_ACCOUNT 1~4 UNIQUENESS. | [WEB SERVICE] 3-2 and 3-6 report query modified with Code level logic | 3-2 (join with CUSTOMER_MASTER), 3-6 (join with CUSTOMER_MASTER)
2 | want to add unique check for BANK_ACCOUNT1~4 in screen 3-8 | [WINDOW APP] added validation to check unique. | 3-8 screen

## 20200828
No | Issue/Changes | Cause/Measures | Similar Screens
1 | Error occur when there is null in CUSTOMER_MASTER BANK_ACCOUNT 1~4 | [WEB SERVICE] Due to usage of trim() method on null values. It is now modifed with null check process | 3-2, 3-6